## Pre-inspection
Startup
[6 empty] | OK | NOK | PENDING
Test unit code | v0.1-pre | Test date | Test engineer | David Redondo
Picture of the unit (Top) |  |  | Checks
|  |  | Board dimensions |  | PENDING
|  |  | Layer copper thickness |  | PENDING
|  |  | Press-fit vias copper thickness |  | PENDING
PENDING
Picture of the unit (Bottom) |  |  |  |  | PENDING
PENDING
PENDING
PENDING

## Startup
Startup
First contact with the board, in which the power delivery, the gate drivers and the current and voltage sensing are thoroughly tested. The electrical behavior of the power modules under switching is assessed. Thermals, mechanical assembly and overall functionality will also be checked.
Test group | Test | Procedure | Material | Acceptance criteria | Result / value |  | Comments | Attachment
Power delivery | LDO Leapers | Populate LDO_HS_A, R401_A, R402_A with Leapers variant values (36kR, 56kR). Solder a dummy 20-40R load in the pads of C406_A. Apply a negative voltage between IN/EN and GND, and measure the voltage at the load terminals. | Power PCB, LDO, resistors, scope, multimeter, power supply | -2V < Vload < -1.8V |  | PENDING
| DCDCs | Populate DCDC_HS_A, DCDC_LS_A. Apply an input voltage of 5V from the LV side and measure VDD and VEE | Same as before, DCDCs | 18V < VDD < 17.8V ; -2V < VEE < -1.8V |  | PENDING
Press-fit | Press-fit module | Install one module (HB_A) as per mounting instructions, check for play. Attach with M2.5x08 screws and check for play. | Same as before, one power module, 3D printed tooling, 4x M2.5x08. | Module sits in snug and tight. |  | PENDING
RGS | RGS pull-down | Populate RGS_HS_A. Apply a positive voltage between gate and source, check the device state across drain and source, then remove one cable. Check the device state across drain and source again. Repeat for RGS_LS_A. Use the power pins to measure resistance | Same as before, RGS_HS_A, RGS_HS_A | Device is in ON state when VGS > 0 and device is in OFF state when VGS is disconnected |  | PENDING
Gate drivers standby | OK and TRIP | Populate U_HS_A, U_LS_A, R302 and R306. Supply the board from the LV side and measure the TRIP and OK nets. | Same as before, U_HS_A, U_LS_A, R302, R306 | Both 5V |  | PENDING
| Standby is OFF | Populate RG_ON_HS, RG_OFF_HS. Supply the board from the LV side and check the device state across drain and source. Repeat for RG_ON_LS, RG_OFF_LS. | Same as before, RG_ON_HS, RG_OFF_HS, RG_ON_LS, RG_OFF_LS | Both devices are in OFF state |  | PENDING
| Enable does not turn on the devices | Supply the board from the LV side and input a 3.3V signal into the ENABLE net. Check the device state across drain and source. | Same as before, 3.3V | Both devices are in OFF state |  | PENDING
| Internal NTC measurement | Without supplying the board, measure the resistance between S_LS and TP409_A. Populate R405_A and power the board. Capture the output signal at TP411. | Same as before, R405_A | Signal is consistent with the SPICE simulation. |  | PENDING
| NTC temperature | Heat up the module from the heatsink side (40degC max) and capture the temperature value and output signal at TP411. Check with simulation. | Same as before, thermal camera | Signal is consistent with the SPICE simulation. |  | PENDING
| PWM to analog | Populate R406_A and C411_A. Capture output signal at TP307. Check with simulation and MATLAB script. | Same as before, R406_A, C411_A | Signal is consistent with the SPICE simulation and MATLAB script. |  | PENDING