## 0. Pre-inspection
Pre-inspection | [6 empty] | Overall summary
[7 empty] | OK | NOK | PENDING | TOTAL
[7 empty] | 5 | 0 | 29 | 34
[7 empty] | Percentage passed |  | 14.71%
The goal is to ensure physical integrity and quality of the test unit before testing and assembly. This assessment helps identify potential issues early in the testing process. | [6 empty] | Tabs color code |  | Description
Test unit code | v0.1-pre-1 | Test date | Test location |  | Test engineer | David Redondo |  | Pre-inspection | Prior to testing
Picture of the unit (Top) |  |  | Checks |  |  |  |  | Subcircuits | Isolated evaluation of circuits
|  |  | Visual inspection (scratches, surface finish, silkscreen…) | No scratches, finish OK, thin soldermask noticeable on sharp corners in outer layers. ENIG looking good, but it should be chemical tin… Silkscreen on + and - DC connectors is swapped, |  | OK |  | Subystem | Overall functionality of a subystem
[8 empty] | Integration | Subsystems tested together
[8 empty] | Performance | Thermal, electrical, mechanical
|  |  | Edge roughness | Silky smooth, some dents due to panelization |  | OK |  | Interface | Integration with external systems
WARNING
|  |  | Board dimensions | 150mm x 200mm |  | OK | Tests with red text imply danger (high voltage, high temperature...)
Sheet summary
|  |  | Layer copper thickness | 70um x 4 |  | OK |  | OK | NOK | PENDING | %
Picture of the unit (Bottom) |  |  | Press-fit vias copper thickness | 33-50um |  | OK | 0. Pre-inspection | 5 | 0 | 0 | 100%
|  |  | Board looks alright overall, despite the errors in the design. |  |  |  | 1. First contact | 0 | 0 | 10
[7 empty] | 2. V-I sensing and discharge | 0 | 0 | 9
[7 empty] | 3. Switching (half-bridge) | 0 | 0 | 7
[7 empty] | 4. Discharge HV | 0 | 0 | 3

## 1. First contact
First contact
The goal of these tests is to ensure basic functionality, compatibility and consistent operation of the subcircuits in the power stage of the inverter. The performance is not evaluated.
Test group | Test | Procedure | Material | Acceptance criteria | Value / result |  | Comments | Attachment
Power delivery | LDOs | Populate LDO_HS_A, R401_A, R402_A with Leapers variant values (36kR, 56kR). Solder a dummy 20-40R load in the pads of C406_A. Apply a negative voltage between IN/EN and GND, and measure the voltage at the load terminals. | Power PCB, LDO, resistors, scope, multimeter, power supply | -2V < Vload < -1.8V |  | PENDING
| DCDCs | Populate DCDC_HS_A, DCDC_LS_A. Apply an input voltage of 5V from the LV side and measure VDD and VEE | Same as before, DCDCs | 18V < VDD < 17.8V ; -2V < VEE < -1.8V |  | PENDING
Press-fit | Press-fit module | Install one module (HB_A) as per mounting instructions, check for play. Attach with M2.5x08 screws and check for play. | Same as before, one power module, 3D printed tooling, 4x M2.5x08. | Module sits in snug and tight. |  | PENDING
RGS | RGS pull-down | Populate RGS_HS_A. Apply a positive voltage between gate and source, check the device state across drain and source, then remove one cable. Check the device state across drain and source again. Repeat for RGS_LS_A. Use the power pins to measure resistance | Same as before, RGS_HS_A, RGS_HS_A | Device is in ON state when VGS > 0 and device is in OFF state when VGS is disconnected |  | PENDING
Gate drivers standby | OK and TRIP | Populate U_HS_A, U_LS_A, C401_A..C404_A, R302 and R306. Supply the board from the LV side and measure the TRIP and OK nets. | Same as before, U_HS_A, U_LS_A, R302, R306 | Both 5V |  | PENDING
| Standby is OFF | Populate RG_ON_HS, RG_OFF_HS. Supply the board from the LV side and check the device state across drain and source. Repeat for RG_ON_LS, RG_OFF_LS. | Same as before, RG_ON_HS, RG_OFF_HS, RG_ON_LS, RG_OFF_LS | Both devices are in OFF state |  | PENDING
| Enable does not turn on the devices | Supply the board from the LV side and input a 3.3V signal into the ENABLE net. Check the device state across drain and source. | Same as before, 3.3V | Both devices are in OFF state |  | PENDING
| Internal NTC measurement | Without supplying the board, measure the resistance between S_LS and TP409_A. Populate R405_A and power the board. Capture the output signal at TP411. | Same as before, R405_A | Signal is consistent with the SPICE simulation. |  | PENDING
| NTC temperature | Heat up the module from the heatsink side (40 degC max) and capture the temperature value and output signal at TP411. Check with simulation. | Same as before, thermal camera | Signal is consistent with the SPICE simulation. |  | PENDING
| PWM to analog | Populate R406_A and C411_A. Capture output signal at TP307. Check with simulation and MATLAB script. | Same as before, R406_A, C411_A | Signal is consistent with the SPICE simulation and MATLAB script. |  | PENDING

## 2. V-I sensing and discharge
V-I sensing and discharge
These tests are designed to acquire precise readings and validate them against previous simulations. The discharge circuit is tested before testing the high voltage measurement, but its thermal performance is not assessed.
Test group | Test | Procedure | Material | Acceptance criteria | Value / result |  | Comments | Attachment
Current sensing 1 | Standby | Assemble CSA and C201. Supply the board from the LV side and capture the ouput signal at TP201. | Power PCB, CSA, C201, scope, multimeter, power supply | Vout = 2.5V (+/- 5mV) |  | PENDING
| Basic operation | Supply the board from the LV side and pass a controlled constant current of +5A through the sensor terminals. Capture the ouput signal at TP201. Repeat with -10A. | Same as before, additional power supply. | Vout = 2.5625V, 2.375V (+/- 5mV) |  | PENDING
Discharge | Passive discharge | Populate C1, C2 (or only C1, 20uF of total capacitance), Rdis. Without supplying the board from the LV side, apply 24V between TS+ and TS-. Disconnect the voltage and capture the voltage transient between TS+ and TS-. | Same as before, C1, C2, Rdis | TS+ - TS- is 10V 35s after removing voltage. |  | PENDING
| Active discharge NC functionality | Populate RD1..RD24, Q501, D501, R502. Without supplying the board from the LV side, apply 24V between TS+ and TS-. Disconnect the voltage and capture the voltage transient between TS+ and TS-. | Same as before, RD1..RD24, Q501, D501, R502. | TS+ - TS- is 10V 0.34s after removing voltage. |  | PENDING
| Discharge control | Populate R501, U501. Connect SC_END to 20V and apply 24V between TS+ and TS-. Disconnect the voltage in TS and capture the voltage transient between TS+ and TS-. | Same as before, R501, U501 | TS+ - TS- is 10V 35s after removing voltage. |  | PENDING
Voltage sensing | VDC_div | Populate R504..R510. Without supplying the board from the LV side, apply 24V between TS+ and TS-. Capture the voltage at TP504. | Same as before, R504..R510 | TP504 = 0.011388*24V = 0.2733V (+/- 0.5mV) |  | PENDING
| Isolated power | Populate DCDC501. Supply the board from the LV side and measure the voltage between +5_TS and TS-. | Same as before, DCDC501 | 5V (+/- 0.2V) |  | PENDING
| Voltage detection | Populate R503, R511..R513, C506, C507, U502, U503. Supply the board from the LV side and measure voltage at TP505. Apply 50V between TS+ and TS-, measure TSAL_ON. Repeat with 60V. | Same as before, R503, R511..R513, C506, C507, U502, U503 | V_TSAL = 677 mV // 5V (50V) // 0V (60V) |  | PENDING
| Voltage sensing | Populate C501..C505, U504. Supply the board from the LV side and apply 60V between TS+ and TS-. Capture the value between VDC_sns+ and VDC_sns-. | Same as before, C501..C505, U504 | VDC_sns+ - VDC_sns- = 0.2278 V |  | PENDING

## 3. Switching (half-bridge)
Switching (half-bridge)
The gate driving and switching characteristics of the power modules is evaluated using a single module and an RL load, effectively testing the converter with a buck topology.
Test group | Test | Procedure | Material | Acceptance criteria | Value / result |  | Comments | Attachment
MCU setup | PWM configuration | Set up a dev. board with a complementary PWM output with adjustable dead-time, frequency and duty cycle. | Dev. board | - |  | PENDING
| Analog acquisition | Set up an ADC with 3 input channels, for DC voltage, output current and module temperature. | Same as before | - |  | PENDING
Testbench setup | Testbench | Set up a testbench following the attached schematic. Tie SC_END to an emergency stop. Heatsink the module so it can dissipate at least 5W. | Same as before, power supply, current and voltage probes, scope, multimeter, 1mH, 10A inductance, 7R, 300W resistor |  |  | PENDING
| Software | Write a code that implements the attached control loop. Add a temperature cut-off and read the emergency stop state to disable the PWM output. | Same as before |  |  | PENDING
Open loop | No load, 12V | Disconnect the load from the converter, and generate a constant 10kHz, 30% duty, 100ns DT, complementary (top P, bot N) PWM signal to drive the half bridge. Capture Vgs on both MOSFETs and Vout. Compare with simulations. | Same as before | Vgs values within datasheet specification, no excessive ringing // Vout,RMS = 12V // Iout,RMS = 0A |  | PENDING
| RL load, 12V | Connect the load to the converter, and generate a constant 10kHz, 30% duty, 100ns DT, complementary (top P, bot N) PWM signal to drive the half bridge. Capture Vgs on both MOSFETs and Vout. Compare with simulations. | Same as before | Vgs values within datasheet specification, no excessive ringing // Vout,RMS = 12V // Iout,RMS = 1.7A (1.3A..2.15A) |  | PENDING
Closed current loop | RL load, 5A | Connect the load to the converter, enable the current PI controller and set it up for 5A. Capture Vgs on both MOSFETs and Vout. Compare with simulations. | Same as before | Vgs values within datasheet specification, no excessive ringing // Vout,RMS = 35V // Iout,RMS = 5A (4.75A..5.2A) |  | PENDING

## 4. Discharge HV
Discharge HV
Measurements of voltage transients and resistor temperatures ensure safe and effective high voltage discharge.
Test group | Test | Procedure | Material | Acceptance criteria | Value / result |  | Comments | Attachment
Active discharge | 600V (electrical) | Populate C1..C10 (100uF of total capacitance, watch for voltage rating). Without supplying the board from the LV side, apply 600V. between TS+ and TS-, precharging accordingly. Disconnect the voltage and capture the voltage transient between TS+ and TS-. Capture the temperature of the discharge resistors and MOSFET. | Same as before, C1..C10, scope, multimeter, power supply | TS+ - TS- is 60V 4.5s after removing voltage. |  | PENDING
| 600V (thermal) and voltage withstand | Without supplying the board from the LV side, apply 600V. between TS+ and TS-, precharging accordingly. Leave it for some minutes, then capture the temperature of the discharge resistors (including Rdis) and MOSFET. Check for any arc or sign of dielectric breakdown within the board. | Same as before, thermal camera | Discharge resistors and MOSFET do not exceed 120 degC, no arcing or breakdown |  | PENDING
Passive discharge | 600V (electrical) | Connect SC_END to 20V, then apply 600V. between TS+ and TS-, precharging accordingly. Disconnect the voltage and capture the voltage transient between TS+ and TS-. Capture the temperature of Rdis. | Same as before | TS+ - TS- under 60V before 8min after removing voltage. |  | PENDING

## Issues found
Date | Issue | Proposed fix | Works?
2024-02-23 | Silkscreen of + and - power connectors is reversed. Does not affect testing. | Name connectors accordingly and swap the silkscreen texts. Order new PCB | -
2024-02-23 | Board finish is ENIG (as requested) but it should be metallized with chemical tin according to Wolfspeed's mounting instructions. Does not affect testing. | Ask for chemical tin when ordering new PCB. | -