## Pre-inspection
Pre-inspection
[6 empty] | OK | NOK | PENDING
The goal is to ensure physical integrity and quality of the test unit before further testing and assembly. This assessment helps identify potential issues early in the testing process.
Test unit code | v0.1-pre-1 | Test date | Test location | Test engineer | David Redondo
Picture of the unit (Top) |  |  | Checks
|  |  | Visual inspection (scratches, surface finish, silkscreen…) |  | PENDING
|  |  | Edge roughness |  | PENDING
|  |  | Board dimensions |  | PENDING
|  |  | Layer copper thickness |  | PENDING
Picture of the unit (Bottom) |  |  | Press-fit vias copper thickness |  | PENDING
PENDING
PENDING
PENDING

## First contact
First contact
The isolated power delivery, the gate drivers and the current and voltage sensing are thoroughly tested. The electrical behavior of the power modules under switching is assessed. Thermals, mechanical assembly of the power modules and overall functionality will also be checked. The goal of this test is to ensure basic functionality and consistent operation of the power stage of the inverter. The performance is not evaluated.
Test group | Test | Procedure | Material | Acceptance criteria | Value / result |  | Comments | Attachment
Power delivery | LDOs | Populate LDO_HS_A, R401_A, R402_A with Leapers variant values (36kR, 56kR). Solder a dummy 20-40R load in the pads of C406_A. Apply a negative voltage between IN/EN and GND, and measure the voltage at the load terminals. | Power PCB, LDO, resistors, scope, multimeter, power supply | -2V < Vload < -1.8V |  | PENDING
| DCDCs | Populate DCDC_HS_A, DCDC_LS_A. Apply an input voltage of 5V from the LV side and measure VDD and VEE | Same as before, DCDCs | 18V < VDD < 17.8V ; -2V < VEE < -1.8V |  | PENDING
Press-fit | Press-fit module | Install one module (HB_A) as per mounting instructions, check for play. Attach with M2.5x08 screws and check for play. | Same as before, one power module, 3D printed tooling, 4x M2.5x08. | Module sits in snug and tight. |  | PENDING
RGS | RGS pull-down | Populate RGS_HS_A. Apply a positive voltage between gate and source, check the device state across drain and source, then remove one cable. Check the device state across drain and source again. Repeat for RGS_LS_A. Use the power pins to measure resistance | Same as before, RGS_HS_A, RGS_HS_A | Device is in ON state when VGS > 0 and device is in OFF state when VGS is disconnected |  | PENDING
Gate drivers standby | OK and TRIP | Populate U_HS_A, U_LS_A, R302 and R306. Supply the board from the LV side and measure the TRIP and OK nets. | Same as before, U_HS_A, U_LS_A, R302, R306 | Both 5V |  | PENDING
| Standby is OFF | Populate RG_ON_HS, RG_OFF_HS. Supply the board from the LV side and check the device state across drain and source. Repeat for RG_ON_LS, RG_OFF_LS. | Same as before, RG_ON_HS, RG_OFF_HS, RG_ON_LS, RG_OFF_LS | Both devices are in OFF state |  | PENDING
| Enable does not turn on the devices | Supply the board from the LV side and input a 3.3V signal into the ENABLE net. Check the device state across drain and source. | Same as before, 3.3V | Both devices are in OFF state |  | PENDING
| Internal NTC measurement | Without supplying the board, measure the resistance between S_LS and TP409_A. Populate R405_A and power the board. Capture the output signal at TP411. | Same as before, R405_A | Signal is consistent with the SPICE simulation. |  | PENDING
| NTC temperature | Heat up the module from the heatsink side (40 degC max) and capture the temperature value and output signal at TP411. Check with simulation. | Same as before, thermal camera | Signal is consistent with the SPICE simulation. |  | PENDING
| PWM to analog | Populate R406_A and C411_A. Capture output signal at TP307. Check with simulation and MATLAB script. | Same as before, R406_A, C411_A | Signal is consistent with the SPICE simulation and MATLAB script. |  | PENDING

## El.measurements and discharge
Electrical measurements and discharge
Test group | Test | Procedure | Material | Acceptance criteria | Value / result |  | Comments | Attachment
Current sensing 1 | Standby | Assemble CSA and C201. Supply the board from the LV side and capture the ouput signal at TP201. | Power PCB, CSA, C201, scope, multimeter, power supply | Vout = 2.5V (+/- 5mV) |  | PENDING
| Basic operation | Supply the board from the LV side and pass a controlled constant current of +5A through the sensor terminals. Capture the ouput signal at TP201. Repeat with -10A. | Same as before, additional power supply. | Vout = 2.5625V, 2.375V (+/- 5mV) |  | PENDING
Discharge | Passive discharge | Populate C1, C2 (or only C1, 20uF of total capacitance), Rdis. Without supplying the board from the LV side, apply 24V between TS+ and TS-. Disconnect the voltage and capture the voltage transient between TS+ and TS-. | Same as before, C1, C2, Rdis | TS+ - TS- is 10V 35s after removing voltage. |  | PENDING
| Active discharge NC functionality | Populate RD1..RD24, Q501, D501, R502. Without supplying the board from the LV side, apply 24V between TS+ and TS-. Disconnect the voltage and capture the voltage transient between TS+ and TS-. | Same as before, RD1..RD24, Q501, D501, R502. | TS+ - TS- is 10V 0.34s after removing voltage. |  | PENDING
| Discharge control | Populate R501, U501. Connect SC_END to 20V and apply 24V between TS+ and TS-. Disconnect the voltage in TS and capture the voltage transient between TS+ and TS-. | Same as before, R501, U501 | TS+ - TS- is 10V 35s after removing voltage. |  | PENDING
| VDC_div | Populate R504..R510. Without supplying the board from the LV side, apply 24V between TS+ and TS-. Capture the voltage at TP504. | Same as before, R504..R510 | TP504 = 0.011388*24V = 0.2733V (+/- 0.5mV) |  | PENDING
PENDING
PENDING
PENDING